## 🏠 Dashboard
🚀 Data Engineering Career Tracker
Your 6-Month Roadmap to becoming a Data Engineer ¦ Target: Oct–Nov 2026
PHASE OVERVIEW
PHASE 1 — Core Skills | PHASE 2 — DE Stack
SQL Advanced · Python ETL PostgreSQL · 3 APIs connected ⏱ Month 1–2 | Apache Airflow · dbt Snowflake · Docker basics ⏱ Month 2–4
PHASE 3 — Cloud + Build | PHASE 4 — Job Ready
AWS S3 · Streamlit Dashboard Deploy live · GitHub portfolio ⏱ Month 4–6 | Resume · Interview prep LinkedIn · Apply to jobs ⏱ Month 6–8
DAILY COMMITMENT
⏰ Weekdays — 1.5 hrs/day 45 min Learn + 45 min Code | 📅 Weekends — 3 hrs/day 1 hr Review + 2 hrs Build
THE 3 RULES
✅ Code every single day — even 20 mins on a busy day | ✅ Push to GitHub every week — your commit history is proof
✅ Finish each stage before jumping to the next — no topic hopping

## 📋 Weekly Checklist
📋 Weekly Task Checklist — Data Engineering Roadmap
Week | Task | Category | Status | Est. Hours | Notes
1 | Create TMDB API account & get API key | Setup | ⬜ Not Started | 0.5
1 | Write Python script to fetch top 10 trending movies | Python | ⬜ Not Started | 1.5
1 | Install PostgreSQL locally | Setup | ⬜ Not Started | 0.5
1 | Create database & first table in PostgreSQL | SQL | ⬜ Not Started | 1
1 | Save API data into PostgreSQL table | Python + SQL | ⬜ Not Started | 1.5
2 | Practice advanced SQL — Window Functions | SQL | ⬜ Not Started | 2
2 | Practice advanced SQL — CTEs | SQL | ⬜ Not Started | 2
2 | Connect Spotify API & pull trending songs | Python | ⬜ Not Started | 2
2 | Connect Jikan API & pull top anime | Python | ⬜ Not Started | 1.5
2 | Push all code to GitHub (first commit!) | GitHub | ⬜ Not Started | 0.5
3 | Write unified ETL script for all 3 APIs | Python | ⬜ Not Started | 3
3 | Clean & deduplicate data with pandas | Python | ⬜ Not Started | 2
3 | Practice SQL on StrataScratch (5 problems) | SQL | ⬜ Not Started | 2.5
4 | Refactor ETL script — modular functions | Python | ⬜ Not Started | 2
4 | Write README for GitHub project | GitHub | ⬜ Not Started | 1
4 | SQL practice — 5 more StrataScratch problems | SQL | ⬜ Not Started | 2.5
5 | Install Docker Desktop | Setup | ⬜ Not Started | 0.5
5 | Run Apache Airflow in Docker | Airflow | ⬜ Not Started | 2
5 | Understand DAGs — read official Airflow docs | Airflow | ⬜ Not Started | 1.5
6 | Convert ETL script into first Airflow DAG | Airflow | ⬜ Not Started | 3
6 | Schedule DAG to run every 6 hours | Airflow | ⬜ Not Started | 1
7 | Install & set up dbt locally | dbt | ⬜ Not Started | 1
7 | Write first dbt model — staging layer | dbt | ⬜ Not Started | 2.5
8 | Write dbt models — transform & mart layer | dbt | ⬜ Not Started | 3
8 | Create free Snowflake trial account | Snowflake | ⬜ Not Started | 0.5
8 | Load data from PostgreSQL into Snowflake | Snowflake | ⬜ Not Started | 2
9 | Build Streamlit dashboard — trending movies | Streamlit | ⬜ Not Started | 3
10 | Add anime & songs tabs to dashboard | Streamlit | ⬜ Not Started | 2.5
10 | Deploy Streamlit app to Streamlit Cloud | Cloud | ⬜ Not Started | 1.5
11 | Create AWS free tier account | AWS | ⬜ Not Started | 0.5
11 | Move raw data storage from local to S3 | AWS | ⬜ Not Started | 2
12 | Set up AWS Glue for transformation | AWS | ⬜ Not Started | 3
12 | Update GitHub README with live app link | GitHub | ⬜ Not Started | 0.5
20 | Start AWS Cloud Practitioner prep | Certification | ⬜ Not Started | 5
22 | Rewrite resume — projects front and center | Job Prep | ⬜ Not Started | 2
22 | Update LinkedIn with DE focus | Job Prep | ⬜ Not Started | 1
23 | Practice explaining projects out loud (record yourself) | Job Prep | ⬜ Not Started | 1.5
24 | Start applying — Junior DE / Analytics Engineer roles | Job Prep | ⬜ Not Started | 3
24 | Prep answers for 'Why DE?' and 'Walk me through your project' | Job Prep | ⬜ Not Started | 2
STATUS KEY: ⬜ Not Started 🔄 In Progress ✅ Done ⏸ Paused

## 📅 Daily Log
📅 Daily Learning Log
Date | Day Type | What I Worked On | Hours Spent | Mood (1-5) | Notes / Blockers
2026-03-15 | Sunday
Weekday
| Weekday |  |  |  |  | Day 2
| Weekday |  |  |  |  | Goal: Write your first real script
| Weekday |  |  |  |  | Open VS Code, create a file called fetch_movies.py
| Weekend |  |  |  |  | Write a Python script that:
| Weekend |  |  |  |  | Connects to TMDB API
| Weekday |  |  |  |  | Fetches top 10 trending movies
| Weekday |  |  |  |  | Prints them in the terminal
| Weekday |  |  |  |  | Install the requests library (pip install requests)
| Weekday |  |  |  |  | ✅ End goal: You see 10 movie names printed in your terminal
| Weekday |  |  |  |  | Day 3
| Weekend |  |  |  |  | Goal: Save data properly
| Weekend |  |  |  |  | Modify your script to save the movie data into a CSV file instead of just printing
| Weekday |  |  |  |  | Fields to save: movie name, release date, rating, popularity score
| Weekday |  |  |  |  | ✅ End goal: A movies.csv file sitting on your desktop with real data
| Weekday |  |  |  |  | Day 4
| Weekday |  |  |  |  | Goal: Learn PostgreSQL basics
| Weekday |  |  |  |  | Open PostgreSQL (use pgAdmin — it has a visual interface)
| Weekend |  |  |  |  | Create a database called entertainment_db
| Weekend |  |  |  |  | Create a table called movies with columns: id, title, release_date, rating, popularity
| Weekday |  |  |  |  | Practice inserting 2–3 rows manually
| Weekday |  |  |  |  | ✅ End goal: A working table in your local database
| Weekday |  |  |  |  | Day 5
| Weekday |  |  |  |  | Goal: Connect Python to PostgreSQL
| Weekday |  |  |  |  | Install psycopg2 library (pip install psycopg2-binary)
| Weekend |  |  |  |  | Modify your script to insert movie data directly into your PostgreSQL table instead of saving to CSV
| Weekend |  |  |  |  | ✅ End goal: Run the script → data automatically goes into your database
| Weekday |  |  |  |  | Day 6 (Weekend — 3 hrs)
| Weekday |  |  |  |  | Goal: Add Spotify API
| Weekday |  |  |  |  | Create a free account at developer.spotify.com → create an app → get API credentials
| Weekday |  |  |  |  | Write a new script fetch_songs.py that pulls top trending songs
| Weekday |  |  |  |  | Save songs into a new table in your database
| Weekend |  |  |  |  | ✅ End goal: Movies AND songs both flowing into your database
| Weekend |  |  |  |  | Day 7 (Weekend — 3 hrs)
| Weekday |  |  |  |  | Goal: Clean up + GitHub
| Weekday |  |  |  |  | Create a free GitHub account if you don't have one
| Weekday |  |  |  |  | Create a new repository called entertainment-pulse
| Weekday |  |  |  |  | Push all your code there
| Weekday |  |  |  |  | Write a basic README — just 5 lines explaining what the project does
| Weekend |  |  |  |  | ✅ End goal: Your project is live on GitHub for the first time
| Weekend |  |  |  |  | Week 2 — Add Anime + Build One Master Script
| Weekday |  |  |  |  | Day 8
| Weekday |  |  |  |  | Goal: Add Jikan API (Anime)
| Weekday |  |  |  |  | Go to jikan.moe — no API key needed, completely free
| Weekday |  |  |  |  | Write fetch_anime.py — pull top 10 anime by rating
| Weekday |  |  |  |  | Save into a third table anime in your database
| Weekend |  |  |  |  | ✅ End goal: 3 data sources all sitting in your database
| Weekend |  |  |  |  | Day 9
| Weekday |  |  |  |  | Goal: Advanced SQL practice
| Weekday |  |  |  |  | Open pgAdmin, write SQL queries on your own data:
| Weekday |  |  |  |  | Find top 5 movies by rating
| Weekday |  |  |  |  | Find anime with popularity above a threshold
| Weekday |  |  |  |  | Join movies and songs by release date
| Weekend |  |  |  |  | Then go to stratascratch.com → solve 3 easy SQL problems
| Weekend |  |  |  |  | ✅ End goal: Hands on SQL with real data you collected yourself
| Weekday |  |  |  |  | Day 10
| Weekday |  |  |  |  | Goal: Build one unified ETL script
| Weekday |  |  |  |  | Create a single file called etl_pipeline.py
| Weekday |  |  |  |  | This one script should call all 3 APIs, clean the data, and load everything into PostgreSQL
No more running 3 separate scripts
💡 Tip: Fill this in every evening — even 2 lines. Consistency compounds. Your future self will thank you. | [5 empty] | ✅ End goal: One command runs your entire pipeline
Day 11
Goal: Clean your data with pandas
Install pandas (pip install pandas)
Read your database tables into pandas dataframes
Handle duplicates, missing values, inconsistent formatting
✅ End goal: Clean, structured data ready for the next stage
Day 12
Goal: SQL practice day
5 more problems on StrataScratch — focus on window functions
Write 3 analytical queries on your own database:
Which day had the most trending movies?
Average rating by genre
Top anime this week vs last week
✅ End goal: Getting comfortable with data analysis on real data
Day 13 (Weekend — 3 hrs)
Goal: Refactor your code properly
Organise your project into folders:
/extractors — API scripts
/loaders — database scripts
/data — raw CSV backups
Add comments to every function explaining what it does
✅ End goal: Clean, professional looking codebase
Day 14 (Weekend — 3 hrs)
Goal: Week 2 review + push to GitHub
Update your GitHub with all new code
Write a proper README with:
What the project does
Tech stack used
How to run it

## 🛠 Project Tracker
🛠 Project Portfolio Tracker
Project Name | Stage | Tech Stack | Status | GitHub Link | Notes
Entertainment Pulse Pipeline | Stage 1 — API Ingestion | Python, PostgreSQL, TMDB/Spotify/Jikan APIs | 🔄 In Progress |  | First project — start here!
Airflow Orchestrated Pipeline | Stage 2 — Automation | Apache Airflow, Docker, dbt, Snowflake | ⬜ Not Started |  | Builds on Project 1
Cloud DE Pipeline | Stage 3 — Cloud | AWS S3, Glue, Redshift, Streamlit | ⬜ Not Started |  | Project 1 migrated to AWS
Finance / Business Data Project | TBD | TBD — use your SimpliSigns background | ⬜ Not Started |  | Leverages your biz experience
OVERALL PORTFOLIO PROGRESS
SQL & Python |  | 0% |  | Update manually as you progress →
Airflow + dbt |  | 0% |  | Update manually as you progress →
Cloud (AWS) |  | 0% |  | Update manually as you progress →
Projects on GitHub |  | 0% |  | Update manually as you progress →
Interview Readiness |  | 0% |  | Update manually as you progress →